Capstone Project Report

Report 2 – Project Management Plan

– Ho Chi Minh City, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	7

1.3 Project Risks	8

2. Management Approach	10

2.1 Project Process	10

2.2 Quality Management	11

2.3 Training Plan	12

3. Project Deliverables	13

4. Responsibility Assignments	14

5. Project Communications	15

6. Configuration Management	16

6.1 Document Management	16

6.2 Source Code Management	16

6.3 Tools & Infrastructures	17

# I. Record of Changes

| Date | A*M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 26/09/2026 | A | Nguyễn Việt Hoàng | Create the first version of Report 2 - Project Management Plan: scope and estimation, objectives, risks, management approach, deliverables, responsibility assignments, communications and configuration management. |

*A - Added    M - Modified    D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

The work breakdown structure below is derived from the Use Case Diagram and the Conceptual ERD delivered with Report 1. Every level-two item names the major feature (FE-xx) or the conceptual entity it implements, so the plan and the requirement model can be traced against each other. Complexity is rated Simple, Medium or Complex, and effort is estimated in man-days for a team of four members working a fourteen-week implementation phase.

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Package 1 - Foundation (Week 1-2) |  | 28 |
| 1.1 | Repository setup, branching strategy and CI/CD pipeline with GitHub Actions | Simple | 4 |
| 1.2 | Docker Compose environment: PostgreSQL, Redis and MinIO object storage | Medium | 5 |
| 1.3 | PostgreSQL schema and Flyway migrations for the eleven conceptual entities (ClipProject, ScriptVersion, FeedbackComment, AI_Request, Composition, Scene, Template, Asset_Media, RenderJob, Clip, Publication) | Complex | 8 |
| 1.4 | FE-01 Login via OAuth / JWT and Logout, including Google OAuth 2.0 and JWT session handling | Complex | 7 |
| 1.5 | Role-based authorization on every endpoint for Writer, Reviewer, Producer and Admin | Medium | 4 |
| 2 | Package 2 - Script & Workflow Core (Week 3-4) |  | 41 |
| 2.1 | FE-02 Create Clip Project and Edit Clip Project, with subject and target grade | Simple | 4 |
| 2.2 | FE-03 Write/Edit Script by Scene with automatic ScriptVersion history and View Script History | Complex | 10 |
| 2.3 | FE-05 Submit Script and the six-state workflow state machine (Draft, Script Review, Approved, In Production, Clip Review, Published) | Complex | 8 |
| 2.4 | FE-05 View Pipeline Board - the state-driven board shared by all authorized users | Medium | 4 |
| 2.5 | FE-07 Review Script with Add Inline Comments, Approve Script and Reject Script | Complex | 7 |
| 2.6 | FE-06 Read & Resolve Feedback for Writer and Producer | Medium | 4 |
| 2.7 | FE-12 Compare Versions of a script across iterations | Medium | 4 |
| 3 | Package 3 - AI Script Intelligence (Week 5-7) |  | 39 |
| 3.1 | FastAPI AI microservice: service skeleton, LLM client and structured-output contract with the core API | Complex | 7 |
| 3.2 | Script-to-scene segmentation with suggested duration and template type | Complex | 8 |
| 3.3 | STEM concept extraction, readability and grade scoring, and terminology or consistency flags | Complex | 8 |
| 3.4 | FE-04 Request AI Assistance and Accept / Ignore AI Suggestions in the scene editor | Medium | 5 |
| 3.5 | Vietnamese TTS narration and automatic caption generation with timing alignment | Complex | 8 |
| 3.6 | AI_Request persistence for cost and usage accounting | Simple | 3 |
| 4 | Package 4 - Remotion Production Pipeline (Week 8-9) |  | 41 |
| 4.1 | Remotion STEM template library: title, formula or step reveal, diagram, data chart, algorithm walk-through, quiz and outro | Complex | 10 |
| 4.2 | FE-08 Open Draft Composition - script-to-Composition mapping into an ordered Scene list | Complex | 8 |
| 4.3 | FE-09 Edit Scene Properties with the form editor and Preview Scene in the embedded Remotion Player | Complex | 9 |
| 4.4 | FE-09 Swap Suggested Assets and Regenerate/Tune AI Narration & Captions | Medium | 5 |
| 4.5 | FE-10 Submit Render Job and Monitor Render Progress: BullMQ and Redis queue, worker pool, headless MP4 rendering | Complex | 9 |
| 5 | Package 5 - Clip Review, QA & Publishing (Week 10-11) |  | 27 |
| 5.1 | FE-11 Review Rendered Clip with Add Timestamp Annotations, Approve Clip and Reject Clip | Complex | 8 |
| 5.2 | FE-11 View Automated Pre-publish QA: duration bounds, caption and audio sync, on-screen text overflow and contrast readability | Complex | 7 |
| 5.3 | FE-13 Publish Clip to YouTube through the YouTube Data API with auto-filled metadata | Complex | 7 |
| 5.4 | FE-14 Browse & Export from Media Library with subject and grade filters | Medium | 5 |
| 6 | Package 6 - Admin, Integration & Testing (Week 12-13) |  | 31 |
| 6.1 | FE-15 Manage Users & Roles | Medium | 4 |
| 6.2 | FE-16 Manage Templates | Medium | 4 |
| 6.3 | FE-17 Monitor Render Queue & Storage and Monitor AI Cost & Usage | Medium | 5 |
| 6.4 | End-to-end integration of the web app, core API, rendering service and AI microservice | Complex | 8 |
| 6.5 | Unit, integration and system testing across all four services | Complex | 10 |
| 7 | Package 7 - Deployment & Documentation (Week 14) |  | 19 |
| 7.1 | Production deployment: Docker images and container workers | Medium | 5 |
| 7.2 | Beta run producing ten or more real STEM clips, with tuning | Medium | 6 |
| 7.3 | Technical documentation, user manual and deployment guide | Medium | 5 |
| 7.4 | Final presentation preparation | Simple | 3 |
| 8 | Project Management (Week 1-14, continuous) |  | 21 |
| 8.1 | Planning, tracking, weekly team and supervisor meetings | Medium | 9 |
| 8.2 | Capstone reports: Project Introduction, Project Management Plan, SRS, Architecture & Database Design, Testing Strategy & Results | Complex | 12 |
|  | Total Estimated Effort (man-days) |  | 247 |

The total estimated effort is 247 man-days. The team has four members and the implementation phase runs for fourteen weeks at five working days per week, which gives a nominal capacity of 280 man-days. The estimate therefore consumes 88 percent of nominal capacity, leaving the remaining margin for rework, defects and the risks listed in section 1.3.

### 1.2 Project Objectives

The overall objective is to deliver a working STEMotion platform that carries a Vietnamese STEM clip through the complete lifecycle - Draft, Script Review, Approved, In Production, Clip Review, Published - with all seventeen major features from Report 1 implemented, and to prove it by producing at least ten real STEM clips during the beta in Package 7. The specific targets below cover quality, time and cost.

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | All documents and all pull requests | 60 | 40% | Peer review before merge; at least one approver per pull request |
| 2 | Unit Test | At least 70% line coverage on the core API and the AI service | 40 | 27% | JUnit 5, Vitest, Pytest; run in CI on every push |
| 3 | Integration Test | All REST endpoints and the render callback | 25 | 17% | Testcontainers with a real PostgreSQL, Redis and MinIO |
| 4 | System Test | All 17 major features FE-01 to FE-17 | 18 | 12% | Scenario-based testing against the Use Case Diagram |
| 5 | Acceptance Test | Ten or more clips produced end to end | 6 | 4% | Run with the supervisor at the end of Package 7 |
|  | Total |  | 149 | 100% |  |

Milestone Timeliness (%)

At least 90 percent of the eight work-package milestones and all report submission dates in section 3 are met on or before the planned date. A milestone missed by more than three working days is escalated at the next supervisor meeting and re-planned in the following iteration.

Allocated Effort (man-days)

| Project Activity | Effort (man-days) | % of total |
| --- | --- | --- |
| Requirement analysis and modelling (use cases, ERD, SRS) | 25 | 10% |
| Design (system architecture, database, API contract, UI/UX) | 27 | 11% |
| Coding and implementation | 123 | 50% |
| Testing (unit, integration, system, acceptance) | 37 | 15% |
| Project management and documentation | 35 | 14% |
| Total | 247 | 100% |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Rendering a 60 to 90 second clip exceeds the five-minute target once several jobs run in parallel | High | Medium | Cache the Remotion bundle between jobs, keep concurrency at one per worker, scale the pool horizontally, and measure render time weekly from Package 4 onwards |
| 2 | LLM API cost or rate limits exceed what the team can fund | Medium | High | Cache AI results per ScriptVersion, use the cheaper model for segmentation, log every AI_Request for cost tracking, and set a monthly cap with an alert |
| 3 | Vietnamese TTS quality is not acceptable for STEM terminology | High | Medium | Evaluate FPT.AI, Google Cloud TTS and an open-source fallback early in Package 3, and keep a manual narration override per scene |
| 4 | YouTube Data API quota or OAuth verification blocks publishing | Medium | Medium | Apply for credentials during Package 1, hide publishing behind an interface, and fall back to manual export from the media library |
| 5 | A team member becomes unavailable through illness, exams or an internship | High | Medium | Give every package a backup owner as shown in section 4, keep all tasks on GitHub Projects, and review load at the weekly meeting |
| 6 | Requirements change after a supervisor review | Medium | High | Work in two-week iterations that end with a demo; record every change in the Record of Changes of the affected report and re-estimate the WBS |
| 7 | The team lacks experience with Remotion and programmatic video | Medium | High | Training plan in section 2.3; one member owns the rendering service from Package 1 and gives a walkthrough to the team |
| 8 | Integration between the four services fails late in the project | High | Medium | Freeze the REST contracts in Package 1, build a thin end-to-end slice by the end of Package 4, and run integration tests in CI from then on |
| 9 | An API key or credential is committed to the repository | High | Medium | Keep every secret in .env excluded from git and in GitHub Actions secrets, enable secret scanning and push protection, and rotate any key that is exposed |
| 10 | Scope creep from features that are attractive but outside the limitations in Report 1 section 6.2 | Medium | Medium | Treat LI-01 to LI-10 as the scope baseline; any addition needs supervisor approval and a re-estimate of the affected package |

## 2. Management Approach

The project is managed with an iterative and incremental approach. The work is split into the eight packages of the WBS; each package is a two-week increment that ends with a working, demonstrable slice of the product and a review with the supervisor. Requirements are captured as UML 2.0 models - the Use Case Diagram and the Conceptual ERD from Report 1 - and each iteration converts a group of use cases from that diagram into running software. Work is tracked on GitHub Projects, changes reach the main branch only through a reviewed pull request, and every report carries its own Record of Changes.

### 2.1 Project Process

The process model is shown in Figure 1. The upper band is the incremental delivery plan: the seven implementation packages run in sequence, each one adding a usable slice on top of the previous. The middle band is the cycle repeated inside every package, and the lower band lists the activities that run continuously across all of them.

Figure 1. The iterative and incremental development process applied to STEMotion.

Plan. The package backlog is taken from the Use Case Diagram: each use case becomes one or more GitHub issues, estimated against the WBS in section 1.1 and assigned an owner from the responsibility matrix in section 4.

Analyse and design. Before coding, the affected part of the ERD, the REST contract and the screen flow are agreed and recorded, so that the four services can be built in parallel without waiting for each other.

Implement. Each issue is developed on its own feature branch with conventional commit messages, and opened as a pull request against the develop branch.

Review and test. Every pull request needs one approving review and a green CI run - build, unit tests and integration tests - before it can be merged.

Demo and accept. At the end of the package the increment is demonstrated to the supervisor. Feedback and change requests are written into the Record of Changes and enter the backlog of the next iteration, which is the feedback loop drawn in red in Figure 1.

### 2.2 Quality Management

Quality is managed at four points in the cycle rather than only at the end. The targets that these activities must reach are the ones tabulated in section 1.2.

- Defect prevention: coding conventions and a shared ESLint, Prettier and Checkstyle configuration enforced in CI; the REST contract and the database schema agreed before implementation starts; database changes only through Flyway migrations so that no environment drifts; all secrets kept out of the repository.

- Reviewing: every document is reviewed by at least one other member before submission, and every pull request needs one approving review. Review comments are resolved in the pull request itself, so the discussion stays with the code.

- Unit testing: JUnit 5 for the Spring Boot core API, Vitest for the React front end and the Node rendering service, and Pytest for the FastAPI AI microservice, targeting at least 70 percent line coverage on the API and the AI service. The suite runs on every push.

- Integration testing: the core API is tested against a real PostgreSQL, Redis and MinIO through Testcontainers, and the render callback path from the rendering service back to the API is tested end to end.

- System testing: scenario-based tests written directly from the Use Case Diagram, so that every one of FE-01 to FE-17 is exercised, including the alternative flows Reject Script and Reject Clip.

- Acceptance testing: the beta in Package 7 produces ten or more real STEM clips through the full lifecycle, reviewed with the supervisor against the non-functional targets from the proposal - AI analysis under 15 seconds, a 60 to 90 second clip rendered in under 5 minutes, dashboards loading in under 3 seconds.

### 2.3 Training Plan

Three of the four technologies in this project are new to most of the team, so training is scheduled inside the packages where the skill is first needed rather than being left to self-study.

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| UML 2.0 modelling with draw.io (use case, ERD, sequence) | All members | Week 1, 1 day | Mandatory |
| Git, GitHub flow, pull requests and GitHub Actions | All members | Week 1, 2 days | Mandatory |
| Spring Boot 3, Spring Security and Spring Data JPA | Trần Nguyễn Hoàng Lê, Phan Thế Trung | Week 1-2, 4 days | Has delivered a secured Spring Boot REST API before |
| React 18, Vite, TypeScript and Tailwind CSS | All members | Week 2, 2 days | Has built a production React application before |
| Docker and Docker Compose | Nguyễn Việt Hoàng, Phan Thế Trung | Week 2, 2 days | Mandatory |
| Remotion: compositions, Player and headless rendering | Nguyễn Việt Hoàng, Phan Phước Long Trì | Week 2 and Week 8, 4 days | Mandatory |
| LLM prompt design and structured output with LangChain | Phan Phước Long Trì, Trần Nguyễn Hoàng Lê | Week 5, 3 days | Mandatory |
| Vietnamese TTS APIs and caption timing alignment | Phan Phước Long Trì | Week 6, 2 days | Mandatory |
| BullMQ and Redis job queues | Nguyễn Việt Hoàng | Week 8, 2 days | Has used a distributed job queue in production |
| YouTube Data API and OAuth 2.0 consent flow | Phan Thế Trung | Week 10, 2 days | Mandatory |

## 3. Project Deliverables

The table below is the master schedule. Week 1 starts on 14/09/2026 and the implementation phase runs for fourteen weeks; the remaining time in the registered duration, up to 03/2027, is reserved as buffer and for defence preparation.

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 - Project Introduction | 25/09/2026 | Includes the Use Case Diagram and the Conceptual ERD |
| 2 | Report 2 - Project Management Plan | 02/10/2026 | This document |
| 3 | Package 1 increment - repository, database schema, Docker environment, authentication and authorization | 27/09/2026 | Internal, demonstrated |
| 4 | Package 2 increment - Script Studio, workflow state machine, review and approval | 11/10/2026 | Internal, demonstrated |
| 5 | Report 3 - Software Requirement Specification | 16/10/2026 | Functional and non-functional requirements, screen flow |
| 6 | Report 4 - System Architecture and Database Design | 30/10/2026 | Render pipeline and AI service data flow, physical schema |
| 7 | Package 3 increment - AI script intelligence, Vietnamese TTS and captions | 01/11/2026 | Internal, demonstrated |
| 8 | Package 4 increment - Remotion template library, scene editor, render queue | 15/11/2026 | First end-to-end MP4 produced |
| 9 | Package 5 increment - clip review, automated QA, YouTube publishing, media library | 29/11/2026 | Internal, demonstrated |
| 10 | Report 5 - Testing Strategy and Results | 11/12/2026 | Test plan, test cases, defect log and coverage |
| 11 | Package 6 increment - admin panel and fully integrated system | 13/12/2026 | Feature complete: FE-01 to FE-17 |
| 12 | Deployment Guide and User Manual | 18/12/2026 | External deliverable |
| 13 | Production deployment and beta with ten or more real STEM clips | 20/12/2026 | Acceptance with the supervisor |
| 14 | Final source code, technical documentation and presentation | 20/12/2026 | Four repositories plus the document set |

## 4. Responsibility Assignments

D ~ Do;  R ~ Review;  S ~ Support;  I ~ Informed;  blank - Omitted

| Responsibility | HoangNVSE182984 | LeTNHSE181662 | TriPPLSE184536 | TrungPTSE184722 |
| --- | --- | --- | --- | --- |
| Project planning and tracking | D | R | R | R |
| Prepare Report 1 - Project Introduction | D | S | R | R |
| Prepare Report 2 - Project Management Plan | D | R | S | R |
| Prepare Report 3 - SRS | R | D | S | S |
| Prepare Report 4 - Architecture and Database Design | D | R | S | R |
| Prepare Report 5 - Testing Strategy and Results | S | R | D | R |
| UML modelling: Use Case Diagram and Conceptual ERD | D | R | S | S |
| Foundation: repository, CI/CD, Docker, database schema | D | S | R | S |
| FE-01 Authentication and role-based authorization | S | D | R | I |
| FE-02 to FE-06 Script Studio and workflow state machine | R | D | S | S |
| FE-07, FE-11, FE-12 Review and approval modules | I | R | S | D |
| FE-04 AI microservice: segmentation and script analysis | S | R | D | S |
| FE-09 Vietnamese TTS narration and captioning | I | S | D | R |
| FE-08 Remotion template library and composition mapping | D | S | R | I |
| FE-09 Production workspace: scene editor and Player preview | D | R | S | S |
| FE-10 Render queue, worker pool and progress reporting | D | I | R | S |
| FE-11 Automated pre-publish QA | R | S | S | D |
| FE-13 YouTube publishing | S | R | I | D |
| FE-14 Media library | S | D | I | R |
| FE-15 to FE-17 Admin panel and monitoring | R | S | I | D |
| Unit and integration testing | R | R | D | S |
| System and acceptance testing | S | D | R | R |
| Deployment and infrastructure | D | R | S | R |
| User manual and deployment guide | S | R | D | R |
| Final presentation | R | D | R | S |

## 5. Project Communications

| Communication Item | Who / Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily stand-up | All four members | Report yesterday, today and any blocker | Every working day, 15 minutes | Online, Discord voice channel |
| Weekly team meeting | All four members | Review the board, re-plan the week, re-estimate if needed | Monday, 60 minutes | Online or on campus, GitHub Projects on screen |
| Supervisor meeting | All four members and Mr. Lại Đức Hùng | Report progress, raise risks, obtain feedback and approval | Weekly, 60 minutes | On campus or Google Meet |
| Iteration demo | All four members and the supervisor | Demonstrate the package increment and collect change requests | End of each package, every two weeks | Google Meet with screen share |
| Code review | Pull request author and one reviewer | Approve a change before it reaches the develop branch | Every pull request, within 24 hours | GitHub pull request review |
| Task and defect tracking | All four members | Assign, track and close work items and defects | Continuous | GitHub Issues and GitHub Projects |
| Build and test notification | All four members | Report a failing build or test immediately after a push | On every push | GitHub Actions, notification to Discord |
| Document review | Author and all members | Review a report before it is submitted | Two days before each due date | Google Docs comments, then Word for the final copy |
| Ad-hoc discussion | All four members | Quick questions and small decisions | As needed | Messenger group chat |

## 6. Configuration Management

### 6.1 Document Management

All project documents are kept in a shared Google Drive folder owned by the team leader, organised into Reports, Meeting Minutes, Diagrams and References. Each document is named FA26SE054_<DocumentName>_v<major>.<minor>, for example FA26SE054_Report2_ProjectManagementPlan_v1.0.

Every report carries the Record of Changes table as its first section. A change is added as a new row with the date, the change type (A for added, M for modified, D for deleted), the person in charge and a description, and the minor version is raised. The major version is raised only when the supervisor accepts the document. Google Drive keeps the full revision history, so any earlier version can be restored, and the accepted copy of each report is also committed to the docs folder of the backend repository so that documents and source code stay together.

Diagrams are stored as editable draw.io files next to the report that uses them and exported to PNG when a report is produced, so the picture in the document and the source of the picture never diverge.

### 6.2 Source Code Management

Source code lives in the GitHub organisation STEMotion-Capstone-FALL-2026 in four repositories: STEMotion_FE for the React web application, STEMotion_BE for the Spring Boot core API, STEMotion_RENDER for the Node.js and Remotion rendering service, and STEMotion_AI for the FastAPI AI microservice.

Each repository follows the same branching model. The main branch always holds a deployable state and is protected: no direct push is allowed. The develop branch holds the current integration state. Work is done on a branch named feature/<issue-number>-<short-description>, or fix/<issue-number>-... for a defect, and reaches develop only through a pull request that has one approving review and a green CI run. At the end of each package, develop is merged into main and tagged v0.<package-number>.

Commit messages follow the Conventional Commits convention (feat, fix, docs, refactor, test, chore) and reference the GitHub issue, so the history can be traced back to a use case. Secrets are never committed: every service reads its configuration from a .env file that is excluded by .gitignore, an .env.example lists the required keys without values, CI reads secrets from GitHub Actions secrets, and secret scanning with push protection is enabled on the organisation. If a credential is ever exposed it is revoked and rotated immediately, as set out in risk 9.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React 18 + Vite + TypeScript + Tailwind CSS (web application); Spring Boot 3.2 / Java 17 (core API); Node.js + Remotion (rendering service); Python FastAPI + LangChain (AI microservice) |
| Database | PostgreSQL 16 (projects, script versions, review states, clip metadata, publishing records); Redis (render queue and cache) |
| Object storage | MinIO, S3-compatible (source assets, narration audio, rendered MP4 files) |
| External services | Google OAuth 2.0 (sign-in); YouTube Data API (publishing); LLM API (segmentation and script analysis); FPT.AI TTS or Google Cloud TTS (Vietnamese narration) |
| IDEs / Editors | IntelliJ IDEA (Java), Visual Studio Code (TypeScript, Python) |
| Diagramming | draw.io (UML use case diagram, conceptual and physical ERD, architecture diagrams) |
| Documentation | Microsoft Office (reports), Google Docs / Sheets / Slides (drafting and review) |
| Version control | GitHub, organisation STEMotion-Capstone-FALL-2026 (source code); Google Drive (documents) |
| CI / CD | GitHub Actions: build, unit and integration tests on every push, Docker image build on merge to main |
| Deployment | Docker and Docker Compose for local and staging; container workers on GCP Cloud Run or AWS EC2 for the render pool |
| Project management | GitHub Projects (backlog, tasks, defects); GitHub Issues (work items); Discord and Messenger (communication) |